## Vendor Outreach Tracker
Murder Mystery Yacht Party - Vendor Outreach Tracker
Event Date: | Summer 2026 (TBD) |  | Capacity: | 400 guests |  | Budget: | $85K-$140K total
Emails Sent: | 6 |  | Awaiting Response: | 6 |  | Last Updated: | 2026-02-05 23:25 PST
Category | Vendor Name | Contact Email | Phone | Email Sent | Status | Response Date | Est. Cost | Quote Amount | Priority | Notes
Yacht Venue | City Experiences | events@cityexperiences.com | (415) 788-8866 | 2026-02-05 23:25 PST | Email Sent |  | $56K-$104K |  | PRIMARY | San Francisco Spirit yacht - 400 capacity. Used for Boots on Deck.
Murder Mystery | The Murder Mystery Company | info@murdermysteryco.com | Via website | 2026-02-05 23:25 PST | Email Sent |  | $5K-$12K |  | PRIMARY | Nation's leader. 8-12 actors, scales to large venues.
AV Production | AVT Productions | info@avtproductions.com | Via website | 2026-02-05 23:25 PST | Email Sent |  | $8K-$15K |  | PRIMARY | Bay Area based. Corporate event specialists.
Murder Mystery | The Dinner Detective | info@thedinnerdetective.com | Via website | 2026-02-05 23:25 PST | Email Sent |  | $4.5K-$10K |  | SECONDARY | True crime approach. Located at The Marker Hotel.
AV Production | MEGA Event Production | info@megaeventproduction.com | Via website | 2026-02-05 23:25 PST | Email Sent |  | $6K-$12K |  | SECONDARY | SF Bay Area. Experience with special events.
Murder Mystery | Epic Immersive | info@epicimmersive.com | Via website | 2026-02-05 23:25 PST | Email Sent |  | $20K-$50K |  | PREMIUM | Unparalleled production. 100+ actors capable. 6-9 month lead.
Yacht Venue | Empress Events | info@empressevents.com | Via website |  | Research Only |  | $150-$200/person |  | BACKUP | The Empress - 150 guests only. Would need 3 yachts.
Yacht Venue | Luxe Cruises | Via website form |  |  | Research Only |  | Unknown |  | BACKUP | Luxury brand. Need to confirm 400+ capacity.
AV Production | Stage Lights and Sound | info@stagelightsandsound.com | Via website |  | Next Wave |  | $7.5K-$14K |  | SECONDARY | Good for yacht events. Marine/outdoor experience.
Event Coordinator | TBD | TBD |  |  | To Be Sourced |  | $2K-$5K |  | REQUIRED | Day-of coordination, vendor management.
Security | TBD | TBD |  |  | To Be Sourced |  | $1.2K-$2K |  | REQUIRED | 4 guards for 400 guests. Crowd management.
Paramedic | TBD | TBD |  |  | To Be Sourced |  | $500-$1K |  | RECOMMENDED | On-site medical support.
Insurance | TBD | TBD |  |  | To Be Sourced |  | $800-$1.5K |  | REQUIRED | Event liability coverage.